## Summary
Bug Summary
Milestone No | Total Fixed Minor Bug | Total Fixed MajorBug | Total Bug | Total Backlog | Total Completed Jira Ticket
Fleetbox Web | 26 | 14 | 40 | 1 | #REF!
Mobile Application | 2 | 0 | 2 | 2
Total | 28 | 14 | 42 | 3

## Present Bugs
Bug No | Jira Ticket No | Bug Titel | Bug Priority | Status | Assign Team | Devoloper Name
1 | M1-123 | No Vehicles Displayed and Search Option Not Working in Catalogues | Major | Not Fixed | FrontEnd | Munimul Islam
2 | M1-133 | No Vehicles are Displayed and Search Option also Not Working in Catalogues -> Exchanges | Major | Not Fixed | FrontEnd | Munimul Islam
3 | M1-136 | In Summary Plans & packages Extras Section "-" &"+" button are not working properly | Minor | Not Fixed | FrontEnd | Munimul Islam
4 | M1-137 | Optional Policy Delete Button is not working properly | Minor | Not Fixed | FrontEnd | Munimul Islam
5 | M1-138 | Pubsilsh Catalogs -> Plans & packages [Protection plan] Before clicking the customize button "Edit selected coverages" button is clickable | Minor | Not Fixed | FrontEnd | Munimul Islam
6 | M1-139 | Latency Issue After Saving Customizations in "Publish Catalogs -> Policies & Agreements" | Minor | Not Fixed | FrontEnd | Munimul Islam
7 | Link | Boundary Value Limit for Location Description in "Service Points" Settings | Minor | Not Fixed | FrontEnd | Munimul Islam
8 | Link | Boundary Value Limit for Location Description in "Locations" Brand Settings | Minor | Not Fixed | FrontEnd | Munimul Islam
9 | Link | Spelling Mistake in Compatibility Questions Answers | Minor | Not Fixed | FrontEnd | Munimul Islam
10 | M1-205 | Resend OTP Not Functioning for Invite Employee Signup | Medium | Not Fixed | FrontEnd | Munimul Islam
11 | M1-204 | Date Selection Fails to Display Tasks for Selected Day | Minor | Not Fixed | FrontEnd | Munimul Islam
12 | M1-204 | Missing Task Time on Task Details Page | Minor | Not Fixed | FrontEnd | Munimul Islam
13 | M1-204 | Task Edit Functionality Not Working | Medium | Not Fixed | FrontEnd | Munimul Islam
14 | M1-204 | Incorrect Assigned Tasks Count in Overview Section on Employee Profile Page | Medium | Not Fixed | FrontEnd | Munimul Islam
15 | Comment | Incorrect Data in API Payload for Dynamic Pricing with Multiple Locations | Medium | Not Fixed | FrontEnd | Munimul Islam
16 | Comment | Optional Fields for Social Links in Links -> Social Links Section | Medium | Not Fixed | FrontEnd | Munimul Islam
17 | M1-229 | Country Flag Mismatch in Brand Info Subsection | Major | Not Fixed | FrontEnd | Munimul Islam
18 | M1-240-Comment | Missing Validation for Change Password Fields in Employee App | Major | Not Fixed | App Developer | Sujit Kumar Sarkar
19 | M1-241 | Frontend Displays Dummy Data Instead of AI Model API Response | Major | Not Fixed | FrontEnd | Munimul Islam
20 | M1-2
21 | M1-2
22 | M1-2
23 | M1-2
24 | M1-2
25 | M1-2
26 | M1-2
27 | M1-2
28 | M1-2
29 | M1-2
30 | M1-2
31 | M1-2
32 | M1-2
33 | M1-2
34 | M1-2
35 | M1-2
36 | M1-2
37 | M1-2
38 | M1-2
39 | M1-2
40 | M1-2
41 | M1-2
42 | M1-2
43 | M1-2
44 | M1-2

## Fixed Bugs
Bug No | Jira Ticket No | Bug Titel | Bug Priority | Status | Assign Team | Developer Name
1 |  | No Space Between "Don’t have an account?" and "Sign up" Options | Minor | Fixed | FrontEnd | Munimul Islam
2 |  | No Space Between "Have an account?" and "Login" Options | Minor | Fixed | FrontEnd | Munimul Islam
3 |  | In Set up your brand page Address 01 and Address02 need to space between Address and 01 | Minor | Fixed | FrontEnd | Munimul Islam
4 |  | Incorrect Error Message When Image Exceeds Size Limit | Minor | Fixed | FrontEnd | Munimul Islam
5 |  | Spacing and Typo Issue Between "Address 02" and "(Optional)" on Brand Setup Page | Minor | Fixed | FrontEnd | Munimul Islam
6 | On Comment | Reminder Title & Notes Input Boundary Value Error | Major | Fixed | FrontEnd | Munimul Islam
7 | On Comment | "Save Changes" Issue When Editing Reminder | Minor | Fixed | FrontEnd | Munimul Islam
8 | On Comment | Reminder : Mileage Input Value Error | Minor | Fixed | FrontEnd | Munimul Islam
9 | On Comment | Show incorrectly schedule after set date in reminder date field | Minor | Fixed | FrontEnd | Munimul Islam
10 | Link | Signup->Set up your brand-> Contact person Issue | Minor | Fixed | BackEnd | Gazi Fayaz Ahmed
11 | Comment Link | Reminder Section: Date & Mileage Remind Value Calculation are wrong | Minor | Fixed | FrontEnd | Munimul Islam
12 | M1-123 | No Vehicles Displayed and Search Option Not Working in Catalogues | Major | Not Fixed | FrontEnd | Munimul Islam
13 | M1-145 | For Designation Delete First OTP does not delete after send Resend OTP | Major | Fixed | BackEnd | Sheikh Shahariar Siam
14 | M1-98 | Task "Download CSV" Button Not Working in "My Team" Section | Major | Not Fixed | FrontEnd | Munimul Islam
15 | M1-133 | No Vehicles are Displayed and Search Option also Not Working in Catalogues -> Exchanges | Major | Not Fixed | FrontEnd | Munimul Islam
16 | M1-136 | In Summary Plans & packages Extras Section "-" &"+" button are not working properly | Minor | Not Fixed | FrontEnd | Munimul Islam
17 | M1-137 | Optional Policy Delete Button is not working properly | Minor | Not Fixed | FrontEnd | Munimul Islam
18 | M1-138 | Publish Catalogs -> Plans & packages [Protection plan] Before clicking the customize button "Edit selected coverages" button is clickable | Minor | Not Fixed | FrontEnd | Munimul Islam
19 | M1-139 | Latency Issue After Saving Customizations in "Publish Catalogs -> Policies & Agreements" | Minor | Not Fixed | FrontEnd | Munimul Islam
20 | M1-143 | Some Cosmetic Bugs in My Team Feature | Minor | Fixed | FrontEnd | Munimul Islam
21 | M1-153 | Some Cosmetic Bugs In Employee Application [03 bugs] | Minor | Fixed | App Developer | Sujit Kumar Sarkar
22 | M1-199 | Default Notifications and Verification Settings for New Accounts | Major | Fixed | BackEnd | Sheikh Shahariar Siam
23 | On Call | Designation Delete OTP does not send | Medium | Fixed | FrontEnd | Sheikh Shahariar Siam
24 | M1-228 | Missing Upgrade Icon in Certain Areas on the Vehicles Page | Medium | Fixed | FrontEnd | Munimul Islam
25 | On call | Customer->Subscription & Brand-> Website Builder don't show update plane | Major | Fixed | FrontEnd | Munimul Islam
26 | M1-98 | Task "Download CSV" Button Not Working in "My Team" Section | Major | Fixed | BackEnd | Sheikh Shahariar Siam
27 | M1-230 | Clicking the Logo Does Not Redirect to the Home Page | Minor | Fixed | FrontEnd | SOUMIK
28 | M1-230 | Add a Default Logo Next to the Phone Number Field | Medium | Fixed | FrontEnd | SOUMIK
29 | M1-230 | Set a Boundary Value for the Phone Number Input Field | Medium | Fixed | FrontEnd | SOUMIK
30 | M1-230 | Redirect to Incompatibility Page for Incompatible VIN | Medium | Fixed | FrontEnd | SOUMIK
31 | M1-230 | Add Proper Email Validation | Medium | Fixed | FrontEnd | SOUMIK
32 | M1-230 | I Can't Find My Car Brand Button Not Functioning | Medium | Fixed | FrontEnd | SOUMIK
33 | M1-230 | Country Selection is Not Mandatory for Proceeding | Major | Fixed | FrontEnd | SOUMIK
34 | Comment | Input Validation for VIN in Check Compatibility | Major | Fixed | FrontEnd | Deepu
35 | M1-230 | Close Phone Number Code Dropdown When Clicking Outside | Minor | Fixed | FrontEnd | Deepu
36 | M1-230 | Clear Cache When User Changes Country | Major | Fixed | FrontEnd | SOUMIK
37 | M1-230 | Country Selection is Not Mandatory for Proceeding | Major | Fixed | FrontEnd | SOUMIK
38 | M1-230 | Add Proper Email Validation on the Not-Compatible Page | Major | Fixed | FrontEnd | SOUMIK
39 | This Function Was Removed | Error in Additional Phone Field in Contact Person Subsection | Major | Fixed | FrontEnd | Munimul Islam
40 |  | Country Field Not Displaying in Brand Info Subsection | Major | Fixed | BackEnd | Habibur Rahman
41 | M1-241 | Frontend Displays Dummy Data Instead of AI Model API Response | Major | Not Fixed | FrontEnd | Munimul Islam
42 | On call | Undesignated Employee show in General Employee section | Medium | Fixed | BackEnd | Sheikh Shahariar Siam
43 | On call | Undesignated Employee Popup Does Not Close When Clicking Outside | Medium | Fixed | FrontEnd | Munimul Islam
44 | Image | When User can send picture without text Show as text N/A | Medium | Fixed | App Developer | Sujit Kumar Sarkar
45 | Image1010 | Owner's Message Received by Fleet Manager as Self-Message | Major | Fixed | BackEnd | Sheikh Shahariar Siam
46 | M1-237 | Automatic Login After Logout then Current Page Refresh | Major | Fixed | FrontEnd | Munimul Islam
47 | Image1011 | "Need Anything" Popup Text Does Not Close After Clicking the X Icon | Minor | Fixed | FrontEnd | Sobuz
48 | Image1012 | Chat Box Does Not Sync in Real-Time | Major | Not Fixed | FrontEnd | Munimul Islam
49 | Image1013 | Create or Reply Conversation API Does Not Work | Medium | Fixed | BackEnd | Sheikh Shahariar Siam
50 | M1-2 |  |  | Fixed
51 | M1-2 |  |  | Fixed
52 | M1-2 |  |  | Fixed
53 | M1-2 |  |  | Fixed
54 | M1-2 |  |  | Fixed
55 | M1-2 |  |  | Fixed
56 | M1-2 |  |  | Fixed
57 | M1-2 |  |  | Fixed
58 | M1-2 |  |  | Fixed
59 | M1-2 |  |  | Fixed
60 | M1-2 |  |  | Fixed
61 | M1-2 |  |  | Fixed
62 | M1-2 |  |  | Fixed
63 | M1-2 |  |  | Fixed
64 | M1-2 |  |  | Fixed
65 | M1-2 |  |  | Fixed
66 | M1-2 |  |  | Fixed
67 | M1-2 |  |  | Fixed
68 | M1-2 |  |  | Fixed
69 | M1-2 |  |  | Fixed
70 | M1-2 |  |  | Fixed
71 | M1-2 |  |  | Fixed
72 | M1-2 |  |  | Fixed
73 | M1-2 |  |  | Fixed
74 | M1-2 |  |  | Fixed
75 | M1-2 |  |  | Fixed
76 | M1-2 |  |  | Fixed
77 | M1-2 |  |  | Fixed
78 | M1-2 |  |  | Fixed
79 | M1-2 |  |  | Fixed
80 | M1-2 |  |  | Fixed
81 | M1-2 |  |  | Fixed
82 | M1-2 |  |  | Fixed
83 | M1-2 |  |  | Fixed
84 | M1-2 |  |  | Fixed
85 | M1-2 |  |  | Fixed
86 | M1-2 |  |  | Fixed
87 | M1-2 |  |  | Fixed
88 | M1-2 |  |  | Fixed
89 | M1-2 |  |  | Fixed
90 | M1-2 |  |  | Fixed
91 | M1-2 |  |  | Fixed
92 | M1-2 |  |  | Fixed
93 | M1-2 |  |  | Fixed
94 | M1-2 |  |  | Fixed
95 | M1-2 |  |  | Fixed
96 | M1-2 |  |  | Fixed
97 | M1-2 |  |  | Fixed
98 | M1-2 |  |  | Fixed
99 | M1-2 |  |  | Fixed
100 | M1-2 |  |  | Fixed

## BackLog
Bug No | Jira Ticket No | Bug Titel | Bug Priority | Status | Assign Team | Devoloper Name
1
2 |  | "Terms of Service" and "Privacy Policy" Pages Do Not Open | Minor | Backlog | FrontEnd | Munimul Islam
3 |  | Dark Mode Not Functioning | Medium | Backlog | App Developer | Sujit Kumar Sarkar
4 |  | Missing Search Option in Inbox Section | Medium | Backlog | App Developer | Sujit Kumar Sarkar
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45

## Jira Ticket Test M1
Jira Ticket Title | Jira Ticket Link | Total Bug Find | Staues
Resent OTP Functionality | Link | 0 | Complete
Forgot Password Functionality | Link | 0 | Complete
Show the proper error messages on registration page | Link | 0 | Complete
Modification required on registration API documentation | Link | 0 | Complete
Authentication Function Login/Register of Admin(Some Dependencies Have been pending, all are complete, but on next milestone the dependencies will be done) | Link | 5 | Complete
Vehicle Reminder Functionality | Link | 4 | Complete
Brand Creating Functionality with Contact Person | Link |  | Complete
vehicle list update API | Link |  | Complete